## Issues
issuekey | Summary | TestStep | Test Data | Test Result | Status Category Changed | Parent | Fix versions | Resolution | Last Viewed | Root cause | Workaround | Time to resolution | Time to first response | Time to close after resolution | Time to review normal change | Priority | Labels | Remaining Estimate | Σ Original Estimate | Affects versions | Linked Issues | Assignee | Assignee-account-id | Status | Components | Responders | Severity | Affected hardware | Planned start | Planned end | Implementation plan | Backout plan | Test plan | Source | Investigation reason | Major incident | Σ Remaining Estimate | Creator | Creator-account-id | Sub-tasks | Request participants | Satisfaction | Satisfaction date | Approvals | Reporter | Request language | Σ Progress | Urgency | Affected services | Pending reason | Approver groups | Work category | Progress | Votes | Issue Type | Time Spent | Total forms | Project | Category | Σ Time Spent | Atlas project key | Atlas project status | Locked forms | Open forms | Submitted forms | Resolved | Work Ratio | Watchers | Created | Sprint | Flagged | Target start | Target end | [CHART] Date of First Response | [CHART] Time in Status | Story point estimate | Issue color | Parent Link | Rank | Updated | Original estimate | Description | Request Type | Epic Link | Start date | Change type | Change risk | Change reason | Security Level | Actual start | Actual end | Team | Organizations | Approvers | Impact | Environment | Due date
AFT-73 | Footer- Checking compatibility with ipad mini and ipad pro | Checking the footer layout and design with ipad mini |  | The layout and design is wrong and erratic and doesn't look good | 2024-04-20T15:27:41.423+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-77,AFT-78,AFT-79,AFT-80,AFT-69,AFT-77,AFT-78,AFT-79,AFT-80 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-20T15:27:40.881+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i0134z: | 2024-04-20T16:46:14.405+0300 |  | Checking the layout desing with ipad mini and ipad pro.Page layout is according to specifications, includes all graphical elements.Checking the functionalities of the links and the google play and app store logo. |  | AFT-63
|  | Checking the footer layout and design with ipad pro |  | The links on the left side are to close to the edge
|  | Checking the functionality of the links on ipad mini |  | The link "How does it work?" it crash the page
|  | Checking the functionality of the links on ipad pro |  | The links works
|  | Checking the functionality of the logos "google play and app store" on ipad mini |  | The logo works they open a new page where the user can download the app
|  | Checking the functionality of the logos "google play and app store" on ipad pro |  | The logo google play work but the app store crash the web site
AFT-72 | Olx Filters - Checking the visual design and font size,type and compatibility | Check visual elements arrangement in layout |  | The layout is according to specifications | 2024-04-20T15:20:04.464+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-74,AFT-75,AFT-76,AFT-66,AFT-74,AFT-75,AFT-76 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-20T15:20:03.868+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i0134j: | 2024-04-20T16:10:25.162+0300 |  | Check visual elements arrangement in layout,font size,typos and compatibility with ipad mini and ipad pro.The user must see the writing clearly and the filters must be written correctly |  | AFT-63
|  | Checking the fost size and typos for the filters |  | The last filter is in ukraine language and the user may not undestand
|  | Checking the layout design,font size and typos with the ipad mini |  | The layout dosen't fit completely on the screen
|  | Checking the layout design,font size and typos with the ipad pro |  | The search button and save search are half off the page
AFT-71 | Olx Header - Buttons functionality and olx logo | Checking the functions of the buttons “add new ad,your account,the heart logo,posts and olx logo” |  | The buttons,logo are working | 2024-04-20T15:14:51.163+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-65 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-20T15:14:50.696+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i0134b: | 2024-04-20T15:14:51.196+0300 |  | Checking the functions of the buttons “add new ad,your account,the heart logo,posts and olx logo” It would be good if something was written on the heart logo so the user for the user to better understand what it means. |  | AFT-63
AFT-70 | Olx Header Design - Checking the logo, colors | Checking the olx desing and colors are according to the documentation provided |  | The colors look clean and the design is good too | 2024-04-20T15:08:48.720+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-64 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-20T15:08:47.820+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i01343: | 2024-04-20T15:08:48.782+0300 |  | Olx Header Design Checking the olx desing and colors are according to the documentation provided. !image-20240420-120653.png¦width=50%,alt="image-20240420-120653.png"! |  | AFT-63
AFT-59 | Contact Information-Contact details of the person who post the ad | We enter in the field "contact person" the name Andrei |  | The text is accepted | 2024-04-09T19:10:27.632+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-62,AFT-42,AFT-62 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T19:10:26.847+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012gr: | 2024-04-14T18:21:35.438+0300 |  | In the contact person field special caracters is not allowed, you can enter at least 3 caracters from the keybord.You can use numbers, and the name you will enter here will be the name that appears in this ad. The email address is entered automatically from the user's account. In the phone number field you need to enter your phone number for the buyers can call you or message you and needs to be a valid phone number. !image-20240409-160956.png¦width=417,height=342,alt="image-20240409-160956.png"! |  | AFT-10
|  | We enter in the contact person field a phone number |  | The text is accepted in the text field
|  | We try to change the email in the field Email address |  | We can't change the email, the email is taken automatic from the user account
|  | We enter a valid phone number in the field phone number |  | The field accept the phone number
|  | We enter an invalid phone number in the field phone number "075687236523425141141142142141" |  | The field accept the invalid phone number
AFT-58 | City field where the user enters the city name or postal code | We enter " Tar" in the text field |  | A dropdown list appear with multiple options | 2024-04-09T19:04:49.173+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-61,AFT-41,AFT-61 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T19:04:47.754+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012gj: | 2024-04-14T18:15:45.772+0300 |  | In this field the user can enter caracters from the keybord, the name of the city or he can use the postal code. If the user enters only the first 2 caracters a list should appear below, but the postal code needs to be completely. !image-20240409-160345.png¦width=403,height=343,alt="image-20240409-160345.png"! |  | AFT-10
|  | We enter a valid postal code "545200" |  | A dropdown list appear with a city to which the postal code belongs
|  | We enter an invalid postal code "54520014353445646" |  | The postal code is accepted but a dopdown list does not appear
AFT-57 | Description-The text box where the user detail the product | We enter 40 caracters in the text field |  | The text field accept the text | 2024-04-09T19:01:23.951+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-40 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T19:01:23.055+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012gb: | 2024-04-09T19:01:24.010+0300 |  | The description text field where the user can detalies the product at least 40 caracters and no more than 9000, the user can use special caracters but not 3 special caracters in a row, numbers, links to other websites are not alowed. !image-20240409-160056.png¦width=822,height=336,alt="image-20240409-160056.png"! |  | AFT-10
|  | We enter 9000 caracters in the text field |  | The text field accept the text
|  | We enter "I am selling a new $4000 car in Spain $#As" |  | The text field accept the text
AFT-56 | Post pictures-Here the user should be able to upload photos | Upload imagines jpg. of 5 mb |  | image accepted and uploaded | 2024-04-09T18:47:05.470+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-39 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T18:47:04.522+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012g3: | 2024-04-09T18:49:52.591+0300 |  | In this section the user can upload pictures for the announcement to be more elaborate so that the buyer can better see what he is selling. The user should able to upload photos of the item is seling by clicking the add images in format of (jpg,jpeg,png,gif) 5mb each in total 8 images. !image-20240409-154504.png¦width=812,height=380,alt="image-20240409-154504.png"! We will check if the button “add imagines” works and it should open a window where the user select the images to upload. !image-20240409-154905.png¦width=826,height=380,alt="image-20240409-154905.png"! We will check if the 2 buttons works, the rotate button and the delete button. |  | AFT-10
|  | Upload imagines jpeg. of 5 mb |  | image accepted and uploaded
|  | Upload imagines png. of 5 mb |  | image accepted and uploaded
|  | Upload imagines gif. of 5 mb |  | image accepted and uploaded
|  | Upload 8 pictures of jpg,jpeg,png,gif according to the documentation |  | the pictures are uploaded
|  | Checking the rotate button of the image |  | the button works,image is rotated
|  | Checking the delete botton |  | the button works, the image is deleted
AFT-55 | Post an ad-The input field and the dropdown field where the user needs to add a title and the dropdown field where the user select the existent category | Add title of 36 caracters | I am selling a car in good condition | the field acepted the title | 2024-04-09T16:31:30.063+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-60,AFT-38,AFT-60 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T16:31:29.054+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012fv: | 2024-04-14T18:00:53.149+0300 |  | The title field where the user needs to put the title of the ad(caracters from the keybord at last 16 caracters and 70 maxim caracters) You can not put in the title (phone,numbers,emails) !image-20240409-133002.png¦width=848,height=240,alt="image-20240409-133002.png"! The dropdown field where the user can select the folowing category like in the pictures below where the put the new ad. !image-20240409-133108.png¦width=1060,height=698,alt="image-20240409-133108.png"! |  | AFT-10
|  | Add title of only numbers betwen 16 - 70 | 15475632154569875 | the field acepted the title
|  | Add link in title | https://www.olx.ro/adding/?bs=homepage_adding | is accepted
|  | Checking the logo functions on categories |  | the logo works and opens more subcategories
|  | Checking several subcategories |  | the subcategories works
|  | In the title field we enter an email |  | The web page crash
AFT-54 | Add new ad-Posting a job, or the user want to sell someting by posting an ad on the web application by click the button add new ad | Click the button "add new ad" |  | the button works and opened a new page | 2024-04-09T16:27:58.878+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-10 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T16:27:57.998+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012fn: | 2024-04-09T16:27:58.915+0300 |  | Checking if the button add new ad works by click it !image-20240409-132552.png¦width=50%,alt="image-20240409-132552.png"! If it works, it should open a new page like in the picture below. !image-20240409-132741.png¦width=1355,height=590,alt="image-20240409-132741.png"! |  | AFT-10
AFT-52 | Remote requirement-The dropdown field should open more option by clicking it | Clicking on view all |  | it opened more options | 2024-04-09T15:15:05.423+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-37 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T15:15:04.371+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012ff: | 2024-04-09T15:15:05.461+0300 |  | In short, virtual recruiting describes a hiring process that takes place remotely, without meeting the candidates face to face. Instead, recruiters rely on technology to host video interviews, virtual events, surveys, and assessments to evaluate their applicants remotely The dropdown field should display more options by clicking the dropdown field, the boxes should be able to be check for the user. !image-20240409-121331.png¦width=202,height=174,alt="image-20240409-121331.png"! When you move the mouse over the boxes and writing, a color should appear where you have the mouse like the picture below !image-20240409-121411.png¦width=194,height=172,alt="image-20240409-121411.png"! |  | AFT-9
|  | Check 1 box and 2 boxes |  | the box stay check
|  | Checking all boxes |  | all boxes stay check and works
|  | Hovering the mouse over the options |  | the background color changes like in the picture in the description
AFT-51 | Open to students-Dropdown field where the user by clicking it will opens two boxes | Clicking on view all |  | it opened more options | 2024-04-09T15:05:06.867+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-36 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T15:05:05.766+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012f7: | 2024-04-09T15:05:06.920+0300 |  | The dropdown field should display more options by clicking the dropdown field, the boxes should be able to be check for the user. !image-20240409-120226.png¦width=206,height=155,alt="image-20240409-120226.png"! When you move the mouse over the boxes and writing, a color should appear where you have the mouse. !image-20240409-120451.png¦width=204,height=156,alt="image-20240409-120451.png"! |  | AFT-9
|  | Check 1 box and 2 boxes |  | the box stay check
|  | Checking all boxes |  | all boxes stay check and works
|  | Hovering the mouse over the options |  | the background color changes like in the picture in the description
AFT-50 | Work schedule-The field by clicking it should show more option for the user | Clicking on view all |  | it opened more options | 2024-04-09T14:58:09.289+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-35 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T14:58:08.415+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012ez: | 2024-04-09T15:10:09.712+0300 |  | The dropdown field should display more options by clicking the dropdown field, the boxes should be able to be check for the user. !image-20240409-115655.png¦width=202,height=347,alt="image-20240409-115655.png"! When you move the mouse over the boxes and writing, a color should appear where you have the mouse !image-20240409-121006.png¦width=198,height=343,alt="image-20240409-121006.png"! |  | AFT-9
|  | Check 1 box and 2 boxes |  | the box stay check
|  | Checking all boxes |  | all boxes stay check and works
|  | Hovering the mouse over the options |  | the background color changes like in the picture in the description
AFT-49 | Type job-By clicking the dropdown field should open more options | Clicking on view all |  | it opened more options | 2024-04-09T14:50:16.254+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-34 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T14:50:15.518+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012er: | 2024-04-09T15:07:59.205+0300 |  | The dropdown field should display more options by cliking the dropdown field, the boxes should be able to be check for the user.When you move the mouse over the boxes and writing, a color should appear where you have the mouse. !image-20240409-120754.png¦width=203,height=356,alt="image-20240409-120754.png"! |  | AFT-9
|  | Check 1 box and 2 boxes |  | the box stay check
|  | Checking all boxes |  | all boxes stay check and works
|  | Hovering the mouse over the options |  | the background color changes like in the picture in the description
AFT-48 | Job mobility-The dropdown field where the user can check the job specifics | Clicking the field "view all" |  | it opens more options | 2024-04-09T14:41:43.710+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-33 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T14:41:42.973+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012ej: | 2024-04-09T15:06:31.107+0300 |  | Will be checking the dropdown field and boxes if you can check 1 or more or none..When you move the mouse over the boxes and writing, a color should appear where you have the mouse !image-20240409-113953.png¦width=25%,alt="image-20240409-113953.png"! !image-20240409-120619.png¦width=202,height=287,alt="image-20240409-120619.png"! |  | AFT-9
|  | Checking 1 and 2 boxes |  | the boxes works
|  | Checking all boxes |  | all boxes stays checked
|  | Hovering the mouse over the text |  | a color appear in the background where you have the mouse
AFT-47 | Call Center-Check the functionality of the button and it should open more categories | Click the button " see all categories" |  | the button works and open more categories | 2024-04-09T14:31:48.289+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-12 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-09T14:31:47.385+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i012eb: | 2024-04-09T15:53:12.626+0300 |  | After click the button “see more categories” should open more options like in the picture below !image-20240409-112235.png¦width=980,height=701,alt="image-20240409-112235.png"! After selecting the call center job it should have 3 more options: -All from jobs -Romanian -Other foreign languages |  | AFT-9
|  | Click the call center-custom support |  | works and openes 3 more options
|  | Selecting all from jobs |  | it opens a new page with all filters
AFT-43 | Main category-Jobs:where the user can search for a specific job by clicking the logo Jobs | Click on the logo jobs to check is functionality and redirected me to the subcategories |  | The logo worked and redirected me to the new page | 2024-04-07T15:22:53.982+0300 |  | Olx Version 2.0 | [8 empty] | Medium |  |  |  |  | AFT-9 |  |  | To Do | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | Andrei Florea_TM2 | [8 empty] | -1 | 1 | 2024-04-07T15:22:53.537+0300 | AFT Sprint 1 | [7 empty] | The Parent Link is only available to Jira Premium users. | 0¦i0126z: | 2024-04-07T15:25:15.161+0300 |  | Here we select the main category jobs and check is functionability for the users to serch for a job,by clicking the logo Jobs it should open a new page. !image-20240407-122450.png¦width=1255,height=486,alt="image-20240407-122450.png"! |  | AFT-9